## Sheet1
List of New Construction under NRHM
S.no. | District | Block | Name of Work | Date/ Month of Work Sanctioned | Financial Progress |  | Name of Execution agency | Physical Progress
[5 empty] | Amount Sanctioned (Rs. In Lakhs) | Expenditure (Rs. In Lakhs |  | Physical Progress | Tentative date of completion
District Hospitals
1 | Amritsar | Amritsar | MCH at Civil Hospital Amritsar | 2012-13 | 901.64 | 305.4 | Punjab Health System Corporation | 35% | 11.11.13
2 |  | Verka | Construction of Drug Ware house at Amritsar | 2013-14 | 141.21 | Nil | Punjab Health System Corporation | Work just started | 6 Month from the date of start
3 | Jalandhar | Jalandhar | MCH at Civil Hospital Jalandhar | 2012-13 | 873.34 | 136.78 | Punjab Health System Corporation | 15% | 29.11.13
4 | Bathinda | Bathinda | MCH at Civil Hospital Bathinda | 2012-13 | 827.36 | 473.82 | Punjab Health System Corporation | 55% | 30.10.13
5 |  | Bathinda | Construction of Drug Ware house at Bathinda | 2013-14 | 116.53 | Nil | Punjab Health System Corporation | Work just started | 6 Month from the date of start
6 | Ludhiana | Ludhiana | Construction of 100 bedded mother and child Hospital Ludhiana. | 2012-13 | 1661.22 | 442.68 | Punjab Health System Corporation | 25% | 06.06.14
7 | MKH Patiala | Patiala | Construction of 100 bedded mother and child Hospital MKH Patiala. (Under centerly sponcered.) | 2012-13 | 1589 | 381.65 | Punjab Health System Corporation | 20% | 31.07.13
8 | Barnala | Barnala | Construction of 50 bedded mother and child Hospital at Barnala | 2012-13 | 882 | Nil | Punjab Health System Corporation | To be opened on 27.06.13 | 12 Month from the date of start
9 | Ferozpur | Ferozpur | Construction of Eye Block at Civil Hospital Ferozpur | 2012-13 | 301.02 | 134.91 | Punjab Health System Corporation | 35% | 30.09.13
10 | Mansa | Mansa | Construction of SNCUat Mansa | 2012-13 | 12.28 | Nil | Punjab Health System Corporation | Tender to be opened on 20.06.13 | 3 Month from the date of start
11 | Gurdaspur | Gurdaspur | Construction of SNCU at Gurdaspur | 2012-13 | 19.11 | Nil | Punjab Health System Corporation | Tender to be opened on 20.06.13 | 3 Month from the date of start
12 | Kapurthala | Kapurthala | Construction of SNCU at Kapurthala | 2012-13 | 31.09 | Nil | Punjab Health System Corporation | Tender to be opened on 20.06.13 | 3 Month from the date of start
13 | Pathankot | Pathankot | Construction of SNCU at Pathankot | 2012-13 | 24.9 | Nil | Punjab Health System Corporation | Tender to be opened on 20.06.13 | 3 Month from the date of start
14 | Ropar | Ropar | Construction of SNCU at Ropar | 2012-13 | 27.92 | Nil | Punjab Health System Corporation | Tender to be opened on 20.06.13 | 4 Month from the date of start
15 | Ajitgarh | Kharar | Construction of Drug Ware house at Kharar | 2012-13 | 118.65 | Nil | Punjab Health System Corporation | Work just started | 6 Month from the date of start
Primary Health Centre
16 | Mansa | Boha | Primary Health Centre at Boha | 2012-13 | 78.05 | 0.39 | Punjab Health System Corporation | 25% | 25.01.14
List of Renovation/ Upgradation under NRHM
District Hospitals
17 | Amritsar | Amritsar | Renovation of DH Amritsar under NABH | 2012-13 | 27.39 | Nil | Punjab Health System Corporation | 10% | 17.07.13
18 | Bathinda | Bathinda | Renovation of DH Bathinda under NABH | 2012-13 | 34.58 | 10.27 | Punjab Health System Corporation | 25% | 31.08.13
19 | Ajitgarh | Ajitgarh | Renovation of DH Mohali under NABH | 2012-13 | 60.36 | 14.27 | Punjab Health System Corporation | 60% | 31.08.13
20 | Ajitgarh | Kharar | Renovation of DH Kharar under ISO | 2012-13 | 16.81 | Nil | Punjab Health System Corporation | Tender to be opened on 27.06.13 | 3 Month from the date of start
21 | Patiala | Patiala | Renovation of DH Rajpura under ISO | 2012-13 | 56.74 | Nil | Punjab Health System Corporation | Tender to be opened on 27.06.13 | 6 Month from the date of start
22 | Sangrur | Sangrur | Renovation of DH Sangrur under ISO | 2012-13 | 37.22 | Nil | Punjab Health System Corporation | Tender to be opened on 27.06.13 | 4 Month from the date of start
23 | Hoshiarpur | Hoshiarpur | Renovation of DH Hoshiarpur under ISO | 2012-13 | 116.72 | Nil | Punjab Health System Corporation | Tender to be opened on 27.06.13 | 6 Month from the date of start
24 |  |  | Upgradation of Maternity wards and Labour room at Hoshiarpur | 2010-11 | 237.58 | 271.7 | Punjab Health System Corporation | 87% | 30.06.13