## Report Engg wing April 2024
Monthly Progress Report of Engg. Wing PHSC for the month of April 2024
S. No. | Name of work | Allotted Cost in Lakhs | Location | Status | Likely Date of completion | Remarks
DISTRICT AMRITSAR
1 | Construction of Food & Drug Administration Zonal office at c | 93.53 | Amritsar | Work in progress. | 30.06.24
2 | Construction of State Cancer Institute at Amritsar | 2631.87 | Amritsar | Work in progress. | 30.06.24 | Ground Floor, F.F & S.F Completed and Inaugrated by Honourable CM on dtd. 17.11.2023.
3 | Construction of Nuclear Medicine block at SCI Amritsar. | 668.36 | Amritsar | Work in progress. | 30.06.24
4 | S I, T & Commissioning of one number 26 passenger lift and one no 15 passenger cum bed elevator lift at State Cancer Institute Amritsar. | 68.55 | Amritsar | Work in progress. | 30.06.24
5 | Repair & Renovation of Nursing School at IMH Amritsar (institute of Mental Health) | 55.8 | Amritsar | Work in progress. | 30.06.24
6 | Construction of New Nursing hostel for 200 students, GMC, Amritsar | 626.56 | Amritsar | Work in progress. | 30.06.24 | Block-I Completed and Inaugrated by Honourable CM on dtd. 17.11.2023.
7 | R/R of Swami Vivekanand Drug-de-Addiction Centre at GMC Amritsar | 80.75 | Amritsar | Work in progress. | 18.08.24
8 | R/R of SDH Baba Bakala Distt. Amritsar | 184.42 | Amritsar | Work in progress. | 31.05.24
9 | 4 No. Lecture Theatre with seating capacity of 300 each Gallery. | 1970.67 | Amritsar | Work in progress. | 30.06.24
| 3 No. Examination Hall with seating capacity of 250 each flat type. |  |  | Work in progress.
| Medical Education Unit |  |  | Work in progress.
10 | Balance work for Addition of 8 New Units at GMC Amritsar | 728.52 | Amritsar | Work in progress. | 14.02.25
11 | Annual Repair & Maintenance of ESI Hospital and Disprnseries at Cluster-3 (ESI Hospital Amritsar Campus) | 100.4 | Amritsar | Work in progress. | 31.03.25
DISTRICT BARNALA
1 | 30 bedded MCH at DH Barnala | 511.29 | Barnala | Work in progress. | 30.10.2024 | Funds approved in PIP FY 2024-25. Work will be completed in 4 months if the funds will be released by 30.06.2024.
2 | Providing & Installation of Fire Fighting and Fire Detection System in CHC Dhanaula | 52.62 | Dhanaula | Work in progress. | 12.09.24
DISTRICT BATHINDA
1 | 30 bedded MCH at DH Bathinda | 680.05 | Bathinda | Work in progress. | 31.07.24 | Funds approved in PIP FY 2024-25. Work will be completed in 1 months if the funds will be released by 30.06.2024.
2 | Construction of 50 bedded Critical care Block at Civil Hospital Bathinda | 1407.47 | Bathinda | Work in progress. | 11.05.25
3 | 30 bedded MCH at SDH Talwandi Saboo | 661.89 | Talwandi Saboo | Work in progress. | 30.09.24 | Funds approved in PIP FY 2024-25. Work will be completed in 3 months if the funds will be released by 30.06.2024.
DISTRICT FARIDKOT
1 | 30 bedded MCH at DH Faridkot | 627.72 | Faridkot | Work in progress. | 31.12.24 | Funds approved in PIP FY 2024-25. Work will be completed in 6 months if the funds will be released by 30.06.2024.
2 | Construction of Blood Bank Centre at DH Faridkot | 10.85 | Faridkot | Work in progress. | 31.05.24
DISTRICT FATEHGARH SAHIB
1 | Repair & Renovation at Distt. Hospital, Fatehgarh Sahib. | 245.98 | Fatehgarh Sahi | Work in progress. | 30.06.24
2 | R/R of Rehabilitation Centre at Bramin Majra Distt. Fatehgarh Sahib | 37.12 | Fatehgarh Sahi | Work in progress. | 17.07.24
3 | Annual Repair & Maintenance of ESI Hospital and Disprnseries at Cluster-2 (ESI Hospital Mandi Gobindgarh) | 58.35 | ESI Hospital Mandi Gobindgarh | Work in progress. | 31.03.25
DISTRICT FAZILKA
1 | Repair/ renovation of DH Fazilka | 139.05 | Fazilka | Work in progress. | 30.06.24
2 | Repair & Renovation of CHC Sitto Gunno | 68.79 | Sitto Gunno | Work in progress. | 31.05.24
DISTRICT GURDASPUR
1 | Balance work of New Construction of 50 Bedded at D.H Gurdaspur. | 808.78 | Gurdaspur | Work in progress. | 14.02.25
2 | Const of Dispensary at Gandhi Nagar Camp Batala (Slum area) Distt. Gurdaspur | 46.15 | Batala | Work in progress. | 31.05.24
3 | Supply, Installation & Commissioning of 15 Passenger 2 no Lifts at DH Gurdaspur & 1 no lift at MCH Batala | 64.22 | Batala | Work in progress. | 30.06.24 | Lift at Gurdaspur installed & Batala work in progress.
DISTRICT HOSHIARPUR
1 | Construction of Food & Drug Administration Zonal office at Hoshiarpur | 55.31 | Hoshiarpur | Work in progress. | 30.06.24
2 | R/R of SDH Mukerian | 109.13 | Sumerian | Work in progress. | 30.06.24
3 | Construction of 6 no. OPD block & General toilet at SDH Dasuya | 54.5 | Dasuya | Work in progress. | 17.07.24
4 | Repair & Renovation at CHC Bhol Kalota | 72.7 | Bhol Kalota | Work in progress. | 30.06.24
DISTRICT JALANDHAR
1 | Supply, Installation & Commissioning of 1 No 20 Passenger lift at DH Kapurthala, SDH Sultanpur Lodhi, MCH Vardhman Ludhiana each hospital & 15 Passenger lift at SDH Phagwara (Group- B) | 101.49 | Sultanpur Lodhi | Work in progress. | 30.06.24 | Lift at Phagwara & Kapurthala Installed. Work at SDH Sultanpur Lodhi in progress.
2 | Supply, Installation & Commissioning of 1 No 15 Passenger Lift at Burn Unit Jalandhar, DDA Centre Jalandhar & Civil hospital Jalandhar each hospital (Group- E) | 59.3 | Jalandhar | Work in progress. | 30.06.24 | Lift at Main Building & Trauma ward installed. Work at Drug de Addiction at Jalandhar in progress.
3 | Repair/ renovation of Drug-de-addiction Centre at DH Jalandhar | 9.61 | Jalandhar | Work in progress. | 31.05.24
4 | Providing & installation of HVAC system in Burn & injury unit at D.H.Jalandhar. | 32.62 | Jalandhar | Work in progress. | 13.07.24
5 | Providing & Installation of Fire Fighting and Fire Detection System in CHC Adampur | 55.72 | Adampur | Work in progress. | 15.09.24
6 | Providing & Installation of Fire Fighting and Fire Detection System in CHC Shankar | 64.69 | Shankar | Work in progress. | 15.09.24
DISTRICT KAPURTHALA
1 | Repair & renovation of Toilets, replace of damaged False Ceiling of MCH and replace of Electrical Cables at MCH Centre & Blood Bank of DH Kapurthala | 24.32 | Kapurthala | Work in progress. | 20.06.24
2 | Construction of approach road to residences & repair of residences at SDH Phagwara | 29.48 | Phagwara | Work in progress. | 20.06.24
3 | Providing & Installation of Fire Fighting and Fire Detection System in CHC Kala Sanghian | 57.46 | Kala Sanghian | Work in progress. | 13.07.24
4 | Providing & Installation of Fire Fighting and Fire Detection System in CHC Begowal | 69.39 | Begowal | Work in progress. | 11.09.24
5 | Addition/Alteration in existing Blood bank at SDH Phagwara | 13.37 | Phagwara | Work in progress. | 15.06.24
DISTRICT LUDHIANA
1 | 100 bedded MCH at DH Ludhiana | 1301.9 | Ludhiana | Work in progress. | 31.01.25
2 | Repair and Renovation at CHC Pakhowal | 47.82 | Pakhowal | Work in progress. | 31.05.24
DISTRICT MALERKOTLA
1 | Civil works for Dialysis unit at DH Malerkotla | 10.46 | Malerkotla | Work in progress. | 31.05.24
2 | R/R of Drug-de-addiction & Rehabilitation Centre at DH Malerkotla | 20.71 | Malerkotla | Work in progress. | 03.07.24
DISTRICT SAS NAGAR
1 | Construction of UPHC at Sector- 69 SAS Nagar | 100.99 | Sector 69, SAS Nagar | Work in progress. |  | The cost of work enhanced, due to revision of drawings. Additional funds have been arranged and work will be start shortly.
2 | External Sewer Work, Strom Water and Rain Harvesting System at Civil Hospital Phase- 6 District SAS Nagar | 144.93 | Phase- 6 District SAS Nagar | Work in progress. | 09.07.24
3 | Repair and Renovation at CHC Dhakauli District SAS Nagar | 50.53 | Dhakauli | Work in progress. | 31.05.24
4 | Planning, Designing, Constructing installing, Testing, Commissioning, Starting UP, Stabilization of ETP with capacity of 50 KLD at PILBS, Phase 3B1 SAS Nagar (along with operation & maintance for five year) | 46.06 | PILBS, Phase 3B1 SAS Nagar | Work in progress. | 21.06.24 | Drawings under approval
5 | Design, Supply, Providing, Installation of Cryogenic LMO Tanks having vessel capacity of 6 KL at PILBS, Phase 3B1, SAS Nagar | 37.41 | PILBS, Phase 3B1 SAS Nagar | Work in progress. | 21.06.24
6 | Construction of Boundary Wall at AIMS Phase- VI, SAS Nagar | 64.12 | AIMS Phase- VI, SAS Nagar | Work in progress. | 06.08.24
7 | Planning, Designing, Constructing installing, Testing, Commissioning, Starting UP, Stabilization of ETP with capacity of 50 KLD at PILBS, Phase 3B1 SAS Nagar (along with operation & maintance for five year) | 34.9 | PILBS, Phase 3B1 SAS Nagar | Work in progress. | 21.08.24
8 | Providing & Installation of Fire Fighting and Fire Detection System in CHC Lalru Distt. SAS Nagar | 57.99 | Lalru | Work in progress. | 12.09.24
9 | Annual Repair & Maintenance of ESI Hospital and Disprnseries at Cluster-1 (ESI Hospital, Phase-7, SAS Nagar) | 55.85 | ESI Hospital, Phase-7, SAS Nagar | Work in progress. | 31.03.25
DISTRICT MUKATSAR SAHIB
1 | 30 bedded MCH at DH Mukatsar Sahib | 841.34 | Mukatsar Sahib | Work in progress. | 31.10.24 | Funds approved in PIP FY 2024-25. Work will be completed in 4 months if the funds will be released by 30.06.2024.
2 | Repair / renovation of SDH Malout | 135.91 | Malout | Work in progress. | 31.05.24
3 | Repair / renovation of SDH Badal | 226.95 | Badal | Work in progress. | 31.05.24
4 | Repair / renovation of Lambi | 60.87 | Lambi | Work in progress. | 31.05.24
5 | Installation of Fire fighting & fire detection system at CHC Lambi | 57.6 | Lambi | Work in progress. | 30.06.24
6 | Construction of Blood Bank at SDH Malout | 21.15 | Malout | Work in progress. | 30.06.24
DISTRICT SBS NAGAR
1 | Construction of 50 bedded Critical care Block at Civil Hospital SBS Nagar | 1254.83 | SBS Nagar | Work in progress. | 06.05.25
DISTRICT PATIALA
1 | Construction of Food & Drug Administration Zonal office at Patiala | 84.51 | Patiala | Work in progress. | 31.05.24
2 | Construction of Blood centre at MKH Patiala District Patiala | 39.38 | Patiala | Work in progress. | 04.10.24 | Site changed. Work will be started after Model code of conduct.
DISTRICT ROOPNAGAR
1 | Construction of Dispenseries (Group I) at Rattangarh | 45.67 | Rattangarh | Work in progress. | 30.06.24
2 | Upgradation of CHC Chamkaur Sahib to SDH | 1050.03 | Chamkaur Sahib | Work in progress. | 30.09.24
3 | R/R of Drug-de-addiction Centre at Roopnagar | 15.3 | Roopnagar | Work in progress. | 17.07.24
4 | Repair & Renovation of RT PCR Lab at DH Roopnagar | 16.94 | Roopnagar | Work in progress. | 31.05.24
DISTRICT SANGRUR
1 | Repair/ renovation of SDH Sunam | 69.15 | Sunam | Work stopped by the agency |  | Work stopped by Agency & LD imposed.
2 | Construction of Blood centre at SDH Sunam Distt. Sangrur | 42.1 | Sunam | Work in progress. | 30.06.24
4 | Special R/R of existing 11 KV sub station alongwith replacement of main electrical control panels, floor panels and LT Cables etc. in DH Sangrur | 40.64 | Sangrur | Work in progress. | 31.05.24
5 | Providing & installation of new tubewell of size 200mm i/d, 150 meter depth at Civil Hospital Sangrur | 23.15 | Sangrur | Work in progress. | 31.05.24 | Bore and assembling of tubewell done. Water sample report awaited.
6 | Providing & Installation of Fire Detection System att SDH Moonak | 73.41 | Moonak | Work in progress. | 12.09.24
7 | R/R of Drug-de-addiction Centre at DH Sangrur | 11.24 | Sangrur | Work in progress. | 06.07.24
DISTRICT TARN TARAN
1 | 30 bedded MCH at SDH Patti | 706.76 | Patti | Work in progress. | 31.09.24 | Funds approved in PIP FY 2024-25. Work will be completed in 3 months if the funds will be released by 30.06.2024.
2 | R/R of Rehabilitation Centre at Bhagupur | 42.9 | Bhagupur | Work in progress. | 03.09.24